## Chart
ACTIVITY TIME CHART FOR ISO 45001:2018 OCCUPATIONAL HEALTH & SAFETY MANAGEMENT SYSTEM - HEXATECH ENGINEERING SDN. BHD. | [18 empty] | UPDATED: 01 SEPT 2026
No. | Activity |  |  | SEPT - DEC 2026
|  | PIC | Target Date * | SEPT 2026 |  |  |  |  | OCT 2026 |  |  |  |  | NOV 2026 |  |  |  |  | DEC 2026
|  |  |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
1 | 45001:2018 System Development, Documentation & Launch | Philip | 01/09/2026 | 1/9
2 | 45001:2018 Awareness & Procedure Training | Philip
3 | Conduct worker consultation, Safety & Health Committee meeting and feedback closure | Philip
4 | Conduct HQ office evacuation drill and representative site emergency drill | Khusairi
5 | Site Safety Plan and HIRARC compilation | Khusairi
6 | Risk Management & HIRARC Assessment Review | Philip
7 | Complete legal and other requirements register and compliance plan review | Philip
8 | 45001:2018 Internal Quality Audit | Philip
9 | Data analysis & objective achievement review | Philip
10 | OHSMS Management Review Meeting | Philip
11 | Pre-certification readiness review | Philip
12 | Stage 1 Adequacy Audit by Certification Body | BV
13 | Stage 2 Certification Audit by Certification Body | BV
14 | Post Stage 2 Certification Audit (Submit corrections and corrective actions for Stage 2 findings) | Philip
15 | ISO 45001:2018 certificate issued under accredited certification | Philip | 30/12/2026 | [19 empty] | 30/12
* Target dates are subject to change.